| Task | Description | Predecessor | Duration (days) |
| --- | --- | --- | --- |
| A | Requirements Analysis | - | 2 |
| B | Feature Definition | A | 2 |
| C | Backend Setup | B | 3 |
| D | Database & Migration | C | 4 |
| E | API Development | D | 4 |
| F | Frontend Setup | B | 3 |
| G | UI Development | F | 5 |
| H | Feature Implementation | G | 4 |
| I | System Integration | E, H | 3 |
| J | Testing & Bug Fixing | I | 4 |
| K | Deployment | J | 1 |

The table above presents the PERT analysis of the project, including task dependencies and estimated durations.

Each task is defined with a fixed duration (deterministic approach), and dependencies indicate the order of execution. Tasks E and H converge into the integration phase, after which testing and deployment are performed.

This structure reflects a real-world software development workflow with parallel frontend and backend development.

| 0 | 2 |
| --- | --- |
| 0 | 2 |

| 2 | 4 |
| --- | --- |
| 2 | 4 |

| 4 | 7 |
| --- | --- |
| 5 | 8 |

| 7 | 11 |
| --- | --- |
| 8 | 12 |

| 11 | 15 |
| --- | --- |
| 12 | 16 |

| 16 | 19 |
| --- | --- |
| 16 | 19 |

| 19 | 23 |
| --- | --- |
| 19 | 23 |

| 23 | 24 |
| --- | --- |
| 23 | 24 |

| 7 | 12 |
| --- | --- |
| 7 | 12 |

| 12 | 16 |
| --- | --- |
| 12 | 16 |

| 4 | 7 |
| --- | --- |
| 4 | 7 |

J

K

I

H

G

F

E

D

C

B

A

*

*

*

*

*

*

*

*

Based on the PERT diagram analysis, the critical path is A – B – F – G – H – I – J – K, resulting in a total project duration of 24 days. Activities on this path have zero slack, meaning any delay will directly affect the project completion time.